## Autofill Version
PREDESIGN SCOPE, BUDGET AND SCHEDULE CONFIRMATION FORM
FACILITY:
PROJECT DESCRIPTION:
JDE PROJECT NUMBER:
DESIGN PROFESSIONAL:
APPROVED CONSTRUCTION BUDGET (1):
(1) If the Approved Construction Budget is not adequate for the proposed scope of work, either determine a recommended Approved Construction Budget for the proposed scope of work or reduce the scope of work to not exceed the Approved Construction Budget.
PROJECT SCHEDULE – All days are calendar days |  |  | Enter Design Start Date Here: | 2023-01-05
Predesign duration (if required) |  | days
SCHEMATIC DESIGN (30%) |  | days | Date due to DASNY: | 2023-01-05
Mailing & Administration | 4 | days | Date to Client: | 2023-01-09
Review | 14 | days
Approval & Administration |  | days
DESIGN DEVELOPMENT (60%) |  | days | Date due to DASNY: | 2023-01-23
Mailing & Administration | 4 | days | Date to Client: | 2023-01-27
Review | 14 | days
Approval & Administration |  | days
100% CONSTRUCTION DOCUMENTS |  | days | Date due to DASNY: | 2023-02-10
Mailing & Administration | 4 | days | Date to QA: | 2023-02-14
Review | 14 | days
Approval & Administration |  | days
BID DOCUMENTS REVISIONS & MAIL |  | days | Date to DASNY CCU: | 2023-02-28
SUBTOTAL DESIGN DURATION | 54 | days
BID PHASE | 45 | days | Estimated Bid Date: | 2023-04-14
CONTRACT AWARD | 45 | days | Construction Start Date: | 2023-05-29
CONSTRUCTION COMPLETION |  | days | Construction Completion Date: | 2023-05-29
CLOSEOUT | 90 | days | Projected Final Payment Date: | 2023-08-27
ESTIMATED PROJECT DURATION | 234 | days
Yellow cells - Input durations in calendar days. |  |  | Blue cells - These cells/dates are self calculating.
Green cells - Standard durations. Revise as required.
Scope Descriptions:
______________________________________ |  |  | _______________________________
DESIGN PROFESSIONAL | DATE |  | DASNY PROJECT MANAGER | DATE
______________________________________ |  |  | _______________________________
CLIENT | DATE |  | DIRECTOR/CHIEF | DATE
Distribution:
Design Professional: |  |  | Project Manager (original):
Client Representative: |  |  | Director/Chief:
Attachments:
Note on E18: = "Design Start" date of Project Information Database (PID)
Note on E32: = "Design Complete" date of Project Information Database (PID)
Note on E34: = "Bid Date" of Project Information Database (PID)
Note on E35: = "Construction Start" date of Project Information Database (PID)
Note on E37: = "Project Close-Out" date of Project Information Database (PID)

## Blank Date Version
PREDESIGN SCOPE, BUDGET AND SCHEDULE CONFIRMATION FORM
FACILITY:
PROJECT DESCRIPTION:
JDE PROJECT NUMBER:
DESIGN PROFESSIONAL:
APPROVED CONSTRUCTION BUDGET (1):
(1) If the Approved Construction Budget is not adequate for the proposed scope of work, either determine a recommended Approved Construction Budget for the proposed scope of work or reduce the scope of work to not exceed the Approved Construction Budget.
PROJECT SCHEDULE – All days are calendar days |  |  | Design Start Date:
Predesign duration (if required) |  | days
SCHEMATIC DESIGN (30%) |  | days | Date due to DASNY:
Mailing & Administration | 4 | days | Date to Client:
Review | 14 | days
Approval & Administration |  | days
DESIGN DEVELOPMENT (60%) |  | days | Date due to DASNY:
Mailing & Administration | 4 | days | Date to Client:
Review | 14 | days
Approval & Administration |  | days
100% CONSTRUCTION DOCUMENTS |  | days | Date due to DASNY:
Mailing & Administration | 4 | days | Date to QA:
Review | 14 | days
Approval & Administration |  | days
BID DOCUMENTS REVISIONS & MAIL |  | days | Date to DASNY CCU:
SUBTOTAL DESIGN DURATION | 54 | days
BID PHASE | 45 | days | Estimated Bid Date:
CONTRACT AWARD | 45 | days | Construction Start Date:
CONSTRUCTION COMPLETION |  | days | Construction Completion Date:
CLOSEOUT | 90 | days | Projected Final Payment Date:
ESTIMATED PROJECT DURATION | 234 | days
Yellow cells - Input durations in calendar days. |  |  | Blue cells - These cells/dates are self calculating.
Green cells - Standard durations. Revise as required.
Scope Description:
______________________________________ |  |  | _______________________________
DESIGN PROFESSIONAL | DATE |  | DASNY PROJECT MANAGER | DATE
______________________________________ |  |  | _______________________________
CLIENT | DATE |  | DIRECTOR/CHIEF | DATE
Distribution:
Design Professional: |  |  | Project Manager (original):
Client Representative: |  |  | Director/Chief:
Attachments:
Note on E18: = "Design Start" date of Project Information Database (PID)
Note on E32: = "Design Complete" date of Project Information Database (PID)
Note on E34: = "Bid Date" of Project Information Database (PID)
Note on E35: = "Construction Start" date of Project Information Database (PID)
Note on E37: = "Project Close-Out" date of Project Information Database (PID)