## Autofill Version
PREDESIGN SCOPE, BUDGET AND SCHEDULE CONFIRMATION FORM
FACILITY:
PROJECT DESCRIPTION:
JDE PROJECT NUMBER:
DESIGN PROFESSIONAL:
APPROVED CONSTRUCTION BUDGET (1):
(1) If the Approved Construction Budget is not adequate for the proposed scope of work, either determine a recommended Approved Construction Budget for the proposed scope of work or reduce the scope of work to not exceed the Approved Construction Budget.
PROJECT SCHEDULE – All days are calendar days |  |  | Enter Design Start Date Here: | 2019-10-11
Predesign duration (if required) |  | days
SCHEMATIC DESIGN (30%) |  | days | Date due to DASNY: | 2019-10-11
Mailing & Administration | 4 | days | Date to Client: | 2019-10-15
Review | 14 | days
Approval & Administration |  | days
DESIGN DEVELOPMENT (60%) |  | days | Date due to DASNY: | 2019-10-29
Mailing & Administration | 4 | days | Date to Client: | 2019-11-02
Review | 14 | days
Approval & Administration |  | days
100% CONSTRUCTION DOCUMENTS |  | days | Date due to DASNY: | 2019-11-16
Mailing & Administration | 4 | days | Date to QA: | 2019-11-20
Review | 14 | days
Approval & Administration |  | days
BID DOCUMENTS REVISIONS & MAIL |  | days | Date to DASNY CCU: | 2019-12-04
SUBTOTAL DESIGN DURATION | 54 | days
BID PHASE | 45 | days | Estimated Bid Date: | 2020-01-18
CONTRACT AWARD | 45 | days | Construction Start Date: | 2020-03-03
CONSTRUCTION COMPLETION |  | days | Construction Completion Date: | 2020-03-03
CLOSEOUT | 90 | days | Projected Final Payment Date: | 2020-06-01
ESTIMATED PROJECT DURATION | 234 | days
Yellow cells - Input durations in calendar days. |  |  | Blue cells - These cells/dates are self calculating.
Green cells - Standard durations. Revise as required.
Comments: _______________________________________________________________________________
______________________________________ |  |  | _______________________________
DESIGN PROFESSIONAL | DATE |  | DASNY PROJECT MANAGER | DATE
______________________________________ |  |  | _______________________________
CLIENT | DATE |  | DIRECTOR/CHIEF | DATE
Distribution:
Design Professional: |  |  | Project Manager (original):
Client Representative: |  |  | Director/Chief:
Institution Representative: |  |  | Construction Technology Group:
Field Representative: |  |  | Director, Procurement:
Attachments: |  |  | Other:
Note on E18: = "Design Start" date of Project Information Database (PID)
Note on E32: = "Design Complete" date of Project Information Database (PID)
Note on E34: = "Bid Date" of Project Information Database (PID)
Note on E35: = "Construction Start" date of Project Information Database (PID)
Note on E37: = "Project Close-Out" date of Project Information Database (PID)

## Blank Date Version
PREDESIGN SCOPE, BUDGET AND SCHEDULE CONFIRMATION FORM
FACILITY:
PROJECT DESCRIPTION:
JDE PROJECT NUMBER:
DESIGN PROFESSIONAL:
APPROVED CONSTRUCTION BUDGET (1):
(1) If the Approved Construction Budget is not adequate for the proposed scope of work, either determine a recommended Approved Construction Budget for the proposed scope of work or reduce the scope of work to not exceed the Approved Construction Budget.
PROJECT SCHEDULE – All days are calendar days |  |  | Design Start Date:
Predesign duration (if required) |  | days
SCHEMATIC DESIGN (30%) |  | days | Date due to DASNY:
Mailing & Administration | 4 | days | Date to Client:
Review | 14 | days
Approval & Administration |  | days
DESIGN DEVELOPMENT (60%) |  | days | Date due to DASNY:
Mailing & Administration | 4 | days | Date to Client:
Review | 14 | days
Approval & Administration |  | days
100% CONSTRUCTION DOCUMENTS |  | days | Date due to DASNY:
Mailing & Administration | 4 | days | Date to QA:
Review | 14 | days
Approval & Administration |  | days
BID DOCUMENTS REVISIONS & MAIL |  | days | Date to DASNY CCU:
SUBTOTAL DESIGN DURATION | 54 | days
BID PHASE | 45 | days | Estimated Bid Date:
CONTRACT AWARD | 45 | days | Construction Start Date:
CONSTRUCTION COMPLETION |  | days | Construction Completion Date:
CLOSEOUT | 90 | days | Projected Final Payment Date:
ESTIMATED PROJECT DURATION | 234 | days
Yellow cells - Input durations in calendar days. |  |  | Blue cells - These cells/dates are self calculating.
Green cells - Standard durations. Revise as required.
Comments: _______________________________________________________________________________
______________________________________ |  |  | _______________________________
DESIGN PROFESSIONAL | DATE |  | DASNY PROJECT MANAGER | DATE
______________________________________ |  |  | _______________________________
CLIENT | DATE |  | DIRECTOR/CHIEF | DATE
Distribution:
Design Professional: |  |  | Project Manager (original):
Client Representative: |  |  | Director/Chief:
Institution Representative: |  |  | Construction Technology Group:
Field Representative: |  |  | Director, Procurement:
Attachments: |  |  | Other:
Note on E18: = "Design Start" date of Project Information Database (PID)
Note on E32: = "Design Complete" date of Project Information Database (PID)
Note on E34: = "Bid Date" of Project Information Database (PID)
Note on E35: = "Construction Start" date of Project Information Database (PID)
Note on E37: = "Project Close-Out" date of Project Information Database (PID)