## Sheet1
Dormitory Authority of New York State
CUNY Hunter N. Auditorium - CM Services
RFP #7578
Questions and Answers to be posted
Question # | Corresponding RFP Section | Question | Answer
1 |  | Please confirm if DASNY experience outside of NYC is considered DASNY experience. | Yes, experience outside of NYC with DASNY is considered DASNY experience.
2 |  | The pre-bid call mentioned future-proofing of the roof and the need to make sure solar panels can be installed at a later date, is this scope only for the roof housing the mechanicals on the 7th floor or is the full roof part of the scope for the CM? | The Architectural design team will detemine the extent of the LL97 and deterime if the lower or upper roof will be affected.
3 | [Ref: DPC, CPC, GCC] | Please advise if there can be a mutual waiver of consequential damages. [Ref: DPC, CPC, GCC] | No.
4 | [Ref CPC XIII.D.1; Appdx. D § 8A-C] | Please advise the CM will be reimbursed for delays beyond the CM’s control [Ref CPC XIII.D.1; Appdx. D § 8A-C] | The CM will be paid for all hours spent on the project that are approved by the DASNY project manager.
5 | [Ref CPC Appdx. A § 14] | Please advise on CM’s schedule responsibilities [Ref CPC Appdx. A § 14] | The CM responsibilities are described in CPC Appendix A § 13
6 |  | Please confirm Professional Pollution liability insurance and Railroad insurance as well as Unmanned aircraft and Marine insurance are required per contract for this CM as agent contract, | This referenced insurances will not be required for the contract. However, they may be required on a case by case basis depending on what work is authorized in subsequent amendments.
7 |  | Will site visits be allowed? | Site visits will not be allowed.
8 |  | Are there preliminary drawings? | There are not any drawings available.
9 |  | How do the GCs relate to the CM? Will CM need to provide? | The CM is an agent of the owner - the standard GC's from DASNY will be used
10 |  | Can you confirm the schedule parameters for the pre con and construction phases? what are the projected start and end dates for each phase . | Exact start and end dates are to be determined. Please refer to the Pre-Proposal Presentation for a proposed construction schedule.
12 |  | When will you be sharing the presentation from the pre-proposal meeting? | A PDF of the presentation has been emailed to everyone that participated in the Pre-Proposal meeting.
13 | Section 1 Project Budget | Please provide project budget for construction hard costs only | 40 million dollars.
14 | Section 3 Tab 4 | Please provide the number of estimates and constructability reviews the CM will be required to perform and the design phases at which the will be performed. | The CM will be reqired to provide their own estimte and reconcile the with the design team estimates at the end of Design Development two (2) or three (3) estimtes and Mid point of Construction Documents two (2) or three (3) estimtes and end of Constrcution Documents phase two (2) or three (3) estimtes.
15 | Section 3 Tab 4 | Does the 36 month construction phase schedule include the close out. | Yes.
16 |  | Please clarify if DASNY is requesting resumes from all names on the organization chart, or only those personnel designated as “key personnel.” | Resumes are required for anyone who will be a member of the project team.
17 |  | Please clarify whether the $40 million is the “Project” budget or the “Construction” budget. | $40M is the construction budget.
18 | Att+D6+B6:D7+B6:D14+D6+B6:D7+B6:D+B6:D23 | Will the project be performed under a PLA Union Labor? | Yes.
19 | Attachment 3 - Construction | Will the work be performed under normal working hours? | Most of the work will be done on normal working hours except for shutdowns and work that may impact other work areas as well as ACM work
20 | Attachment 3 - Construction | Will there be a need for any community relations/outreach/notifications, related to street closures logistics, for residents on 69th street | There may be some, but most of it will be handled by school community relations group
21 | Attachment 3 - Construction | What level of detail will be required for the schedule to be submitted for the project as part of the RFP? | Milestone schedule only
22 | Attachment 3 - Construction | Will there be Hazmat work associated with the project? | Yes.
23 | Attachment 3 - Construction | Where there be a "Made in America" clause in the specifications? | Steel
24 | Attachment 3 - Construction | Will there be commissioning as part of the contract? | Yes.
25 | Attachment 3 - Construction | Is the closeout of the project included in the overall schedule/ | Yes.
26 | Attachment 3 - Construction | Will DASNY provide a CM office within the facility? | Field Office will be arranged with Facility near or in the work area
27 | Attachment 3 - Construction | Access to freight elevator and hours operations? | Freigh elevator needs to be coordinated with facility and mostly to be used early morning
28 | Attachment 3 - Construction | Will CUNY/DASNY provide COVID safety protocols if necessary, at commencement of construction? | CUNY/DASNY covid regulations will be provided at time of bid
29 | Attachment 2 - Design/Predesign | When will the schematic design documents be available? | On or about June 1st.
30 | Attachment 2 - Design/Predesign | Will there be a project management virtual platform virtual platform for uploading and dowloading of drawings, specs, review comments, reports, etc? | Yes
| Attachment 2 - Design/Predesign | What will the submission cycles be for constructability and value engineering review? | 60% and 90%
| Attachment 3 - Construction | Will there be a smoke evacuation system as part of the upcoming project? | Too early in the proejct to determine.
| Attachment 3 - Construction | Provide use/type of buidling space in the vicinity of the auditorium? | The auditorium is located at the base of the north building. Which is a 14 story academic building. There are classrooms above the auditorium.
| Attachment 3 - Construction | Will the above spaces remain active during construction and what kinds of restrictions related to noise, dust, and construction activities can we expect? | Classes will remain in use during construction.
| Section 3.2 - Page limit | Does the 100 page limit also include any sample reports being requested? | Total package must be within 100 page limit